## Ark1
PROJECT SCHEDULE FOR:
LOFTHUS FRUKT OG SAFT
PROJECT START 18.11.2019
PROJECT END 18.11.2019
DAYS TOTAL: 20
Project Manager: Eric | Front-end developer: Hassan
Designer: Maria | Marketing director: Simon
Copyrighter: Nany | Day off
TASK | LEAD ROLE | START | END | DAYS | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 1 | [6 empty] | WEEK 1
PLANNING |  | 2019-11-11 | 2019-11-15 |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Project Start Meeting | Eric | 2019-11-11 | 2019-11-11 | 1 | bar: WEEK 1 M
Market Research | Simon | 2019-11-12 | 2019-11-14 | 3 | bar: WEEK 1 T to WEEK 1 T
Site Outline | Maria | 2019-11-12 | 2019-11-14 | 3 | bar: WEEK 1 T to WEEK 1 T
Concept Development | Hassan | 2019-11-13 | 2019-11-15 | 3 | bar: WEEK 1 W to WEEK 1 F
Site Structure | Maria | 2019-11-14 | 2019-11-15 | 2 | bar: WEEK 1 T to WEEK 1 F
DESIGN |  | 2019-11-18 | 2019-11-22
Design Meeting | Eric | 2019-11-18 | 2019-11-18 | 1 | bar: WEEK 2 M
Style Tiles | Maria | 2019-11-18 | 2019-11-19 | 2 | bar: WEEK 2 M to WEEK 2 T
Wireframe | Maria | 2019-11-18 | 2019-11-20 | 3 | bar: WEEK 2 M to WEEK 2 W
Portfolio Images | Maria | 2019-11-19 | 2019-11-21 | 3 | bar: WEEK 2 T to WEEK 2 T
Typography & Readability | Maria | 2019-11-20 | 2019-11-22 | 3 | bar: WEEK 2 W to WEEK 2 F
Copyright | Nany | 2019-11-20 | 2019-11-22 | 3 | bar: WEEK 2 W to WEEK 2 F
BUILD |  | 2019-11-25 | 2019-11-29
Customer Approval Meeting | Eric | 2019-11-25 | 2019-11-25 | 1 | bar: WEEK 1 M
HTML and CSS | Hassan | 2019-11-25 | 2019-11-26 | 2 | bar: WEEK 1 M to WEEK 1 T
Implementing Javascript | Hassan | 2019-11-27 | 2019-11-28 | 2 | bar: WEEK 1 W to WEEK 1 T
Payment Gateway Integration | Hassan | 2019-11-29 | 2019-11-29 | 1 | bar: WEEK 1 F
Add Tect and Photos to Website | Maria | 2019-11-29 | 2019-11-29 | 1 | bar: WEEK 1 F
LAUNCH |  | 2020-01-02 | 2020-01-06
Lauch Meeting | Eric | 2020-01-02 | 2020-01-02 | 1 | bar: WEEK 1 M
Cross Platform and Browser Testing | Hassan | 2020-01-02 | 2020-01-03 | 2 | bar: WEEK 1 M to WEEK 1 T
Key meetings with customer and presentations | Eric | 2020-01-02 | 2020-01-03 | 2 | bar: WEEK 1 M to WEEK 1 T
Bug Fixes | Hassan | 2020-01-03 | 2020-01-04 | 2 | bar: WEEK 1 T to WEEK 1 W
Lauch Site | Hassan | 2020-02-05 | 2020-01-06 | 2 | bar: WEEK 1 T to WEEK 1 F